## Gantt Chart Template
| PROJECT TITLE | Utah Valley University 3D Interactive Map |  |  |  | COMPANY NAME | [8 empty] | Colin Studios
| PROJECT MANAGER | Colin Hite |  |  |  | DATE | [8 empty] | 2019-01-12
[6 empty] | 01/14 - 01/20 |  |  |  |  | 01/21 - 01/27 |  |  |  |  | 01/28 - 02/03 |  |  |  |  | 02/04 - 02/10 |  |  |  |  | 02/11 - 02/17 |  |  |  |  | 02/18 - 02/24 |  |  |  |  | 02/25 - 03/03 |  |  |  |  | 03/04 - 03/10 |  |  |  |  | 03/11 - 03/17 |  |  |  |  | 03/18 - 03/24 |  |  |  |  | 03/25 - 03/31 |  |  |  |  | 04/01 - 04/07 |  |  |  |  | 04/08 - 04/14 |  |  |  |  | 04/15 - 04/21 |  |  |  |  | 04/22 - 04/28 |  |  |  |  | 04/29 - 05/05
[6 empty] | MILESTONE ONE | [19 empty] | MILESTONE TWO | [19 empty] | MILESTONE THREE | [19 empty] | MILESTONE FOUR
TASK NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Modeling | 2019-01-07 | 2019-03-31 | 84 | bar: WEEK 1 M to WEEK 9 R; WEEK 13 W to WEEK 16 W
1.1 | CS Building | 2019-01-15 | 2019-02-10 | 25 | 100% | bar: WEEK 1 M to WEEK 7 F
1.1.1 | Circular Fire Alarm |  |  | 1 | 100% | bar: WEEK 3 F
1.1.2 | CS Elevator |  |  | 7 | 100% | bar: WEEK 4 M to WEEK 4 T
1.1.3 | Metal Door Variant 1 |  |  | 1 | 100% | bar: WEEK 1 W
1.1.4 | Giant Metal Pipe |  |  | 1 | 100% | bar: WEEK 2 M
1.1.5 | Wall Fire Alarm |  |  | 1 | 100% | bar: WEEK 3 R
1.1.6 | Square Fire Alarm |  |  | 1 | 100% | bar: WEEK 3 M
1.1.7 | Big Metal Pipe |  |  | 1 | 100% | bar: WEEK 1 F
1.1.8 | AED Box |  |  | 1 | 100% | bar: WEEK 2 F
1.1.9 | Newspaper Stand |  |  | 1 | 100% | bar: WEEK 4 F
1.1.10 | Metal Door Variant 2 |  |  | 1 | 100% | bar: WEEK 3 W
1.1.11 | Chair |  |  | 1 | 100% | bar: WEEK 4 W
1.1.12 | Air Conditioning Vent |  |  | 1 | 100% | bar: WEEK 2 R
1.1.13 | Info Flag |  |  | 1 | 100% | bar: WEEK 1 T
1.1.14 | Firehydrant Box |  |  | 1 | 100% | bar: WEEK 3 T
1.1.15 | Couch Variant 1 |  |  | 1 | 100% | bar: WEEK 2 W
1.1.16 | Drinking Fountain |  |  | 3 | 100% | bar: WEEK 4 F
1.1.17 | Flyer Wall Mount |  |  | 1 | 100% | bar: WEEK 2 T
1.1.18 | Clock |  |  | 1 | 100% | bar: WEEK 1 M
1.1.19 | Celing Light Variant 2 |  |  | 1 | 100% | bar: WEEK 1 R
1.1.20 | Wooden Door Variant 2 |  |  | 1 | 100% | bar: WEEK 4 R
1.2 | CB Building | 2019-02-04 | 2019-03-04 | 30 | 0% | bar: WEEK 4 M to WEEK 8 M
1.3 | FL Building | 2019-02-18 | 2019-03-17 | 29 | 0% | bar: WEEK 6 M to WEEK 9 F
1.4 | LA Building | 2019-03-04 | 2019-03-31 | 27 | 0% | bar: WEEK 8 M to WEEK 11 R
2 | Texturing | 2019-02-11 | 2019-03-31 | 50 | bar: WEEK 1 M to WEEK 7 R; WEEK 14 M to WEEK 16 W
2.1 | CS Building | 2019-02-11 | 2019-03-03 | 22 | 0% | bar: WEEK 5 M to WEEK 7 F
2.2 | CB Building | 2019-02-25 | 2019-03-17 | 22 | 0% | bar: WEEK 7 M to WEEK 9 F
2.3 | FL Building | 2019-03-04 | 2019-03-24 | 20 | 0% | bar: WEEK 8 M to WEEK 10 F
2.4 | LA Building | 2019-03-11 | 2019-03-31 | 20 | 0% | bar: WEEK 9 M to WEEK 11 F
3 | Sound Design | 2019-03-25 | 2019-04-14 | 19 | bar: WEEK 1 M to WEEK 7 R; WEEK 13 R to WEEK 16 W
3.1 | UI Sound Effects | 2019-03-25 | 2019-04-07 | 12 | 0% | bar: WEEK 11 M to WEEK 12 F
3.2 | CS Building Sound Effects | 2019-04-01 | 2019-04-07 | 6 | 0%
3.3 | CB Building Sound Effects | 2019-04-01 | 2019-04-07 | 6 | 0%
3.4 | FL Building Sound Effects | 2019-04-08 | 2019-04-14 | 6 | 0% | bar: WEEK 13 M to WEEK 13 F
3.5 | LA Building Sound Effects | 2019-04-08 | 2019-04-14 | 6 | 0% | bar: WEEK 13 M to WEEK 13 F
4 | Scripting | 2019-03-11 | 2019-05-01 | 50 | bar: WEEK 1 M to WEEK 7 W; WEEK 13 W to WEEK 16 W
4.1 | Navigation Script | 2019-03-11 | 2019-03-25 | 14 | 0% | bar: WEEK 9 M to WEEK 11 M
4.2 | Player Navigation Script | 2019-03-11 | 2019-03-25 | 14 | 0% | bar: WEEK 9 M to WEEK 11 M
4.3 | Elevator Script | 2019-03-31 | 2019-04-09 | 9 | 0% | bar: WEEK 12 M to WEEK 13 T
4.4 | Player Teleport Script | 2019-03-31 | 2019-04-09 | 9 | 0% | bar: WEEK 12 M to WEEK 13 T
4.5 | Mini Map | 2019-03-31 | 2019-04-09 | 9 | 0% | bar: WEEK 12 M to WEEK 13 T
4.6 | Pause Scipt | 2019-03-31 | 2019-04-09 | 9 | 0% | bar: WEEK 12 M to WEEK 13 T
4.7 | Time Estimate Script | 2019-03-28 | 2019-03-30 | 2 | 0% | bar: WEEK 11 R to WEEK 11 F
4.8 | Exit Game Script | 2019-03-26 | 2019-03-27 | 1 | 0% | bar: WEEK 11 T to WEEK 11 W
5 | User Interface | 2019-03-11 | 2019-04-07 | 26 | bar: WEEK 1 M to WEEK 7 R; WEEK 13 R to WEEK 16 W
5.1 | Intro | 2019-03-11 | 2019-03-14 | 3 | 0% | bar: WEEK 9 M to WEEK 9 W
5.2 | Main Menu | 2019-03-15 | 2019-03-18 | 3 | 0% | bar: WEEK 9 R to WEEK 9 F
5.3 | About | 2019-03-19 | 2019-03-22 | 3 | 0% | bar: WEEK 10 M to WEEK 10 W
5.4 | How To | 2019-03-23 | 2019-03-26 | 3 | 0% | bar: WEEK 10 R to WEEK 10 F
5.5 | Pause | 2019-03-27 | 2019-03-30 | 3 | 0% | bar: WEEK 11 M to WEEK 11 T
5.6 | Mini Map | 2019-03-31 | 2019-04-03 | 3 | 0% | bar: WEEK 11 W to WEEK 11 F
5.7 | Info Slides | 2019-04-04 | 2019-04-07 | 3 | 0% | bar: WEEK 12 M to WEEK 12 T
5.8 | Building Navigation | 2019-04-04 | 2019-04-07 | 3 | 0% | bar: WEEK 12 W to WEEK 12 F
6 | Lighting | 2019-03-11 | 2019-05-01 | 50 | bar: WEEK 1 M to WEEK 7 R; WEEK 13 R to WEEK 16 W
6.1 | CS Building | 2019-03-11 | 2019-03-24 | 13 | 0% | bar: WEEK 9 M to WEEK 10 F
6.2 | CB Building | 2019-03-25 | 2019-04-07 | 12 | 0% | bar: WEEK 11 M to WEEK 12 F
6.3 | FL Building | 2019-04-01 | 2019-04-14 | 13 | 0% | bar: WEEK 12 M to WEEK 13 F
6.4 | LA Building | 2019-04-08 | 2019-04-21 | 13 | 0% | bar: WEEK 13 M to WEEK 14 F